## Sheet1
Programming | Days | Art | Days | Design | Days | Q/A | Days
Character Controller | 5 | Warrior model | 5 | Town hub level | 5 | Gameplay testing | 10
RPG Framework | 10 | Mage model | 5 | Wilderness level | 10 | Warrior skill progression test | 10
AI | 10 | Town hub props | 10 | Catacombs level | 10 | Mage skill progression test | 10
Skill Tree system | 3 | Wilderness props | 10 | Town quests and dialog | 3 | Equipment table/drop rate tests | 10
Warrior skills | 5 | Catacombs level pieces | 5 | Wilderness quests and dialog | 5 | Quest Line tests | 5
Mage skills | 5 | Catacombs props | 10 | Catacombs quests and dialog | 5 | Localisation | 5
Equipment system | 3 | Goblin Warrior | 5 | Warrior skills | 5
In game HUD | 3 | Goblin Shaman | 5 | Mage Skills | 5
Inventory UI | 5 | Weapon models | 5 | Equipment tables | 5
Stores & Stores UI | 3 | Warrior Animations | 10 | Goblin AI & Skills | 3
Quest system | 4 | Mage Animations | 10 | Raven Witch boss AI/skills | 3
Quest UI | 3 | HUD Textures | 5 | Talos boss AI/skills | 3
Main Menu | 1 | Quest UI textures | 2 | UI Design | 3
Options | 1 | Inventory UI | 3 | Localisation | 5
Localisation | 5 | Warrior skill particle FX | 5
|  | Mage skill particle FX | 5
|  | Talos Boss character | 10
|  | Blood Raven boss character | 10
|  | Skill Icons | 2
|  | Inventory Icons | 3
|  | Loot drop models | 5
|  | Localisation | 5
| 66 |  | 135 |  | 70 |  | 50
Vertical slice should take around 13 weeks with 1 programmer, 1 designer and 2 artists full time and 1 part time Q/A tester
Allowed a few days for each department to cater for localisation in the vertical slice.
Localisation will become more of a priority when the full game gets closer to release.